## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | eSchool : Learning management system |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(Information Technology)
PROJECT GUIDE |  | Poonam Pangarkar |  |  |  |  | DATE | [6 empty] | 2022-10-11
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [44 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Aman Dhumal, Pranjal Desai, Dhanashree kasar, Om jondhale | 16/1/23 | 24/1/23 | 2 | 100% | bar: WEEK 1 M to WEEK 2 F
1.2 | Identifying the functionalities of the Mini Project | Aman Dhumal , Pranjal Desai | 24/1/23 | 2023-01-31 | 1 | 100% | bar: WEEK 3 M to WEEK 4 F
1.3 | Discussing the project topic with the help of paper prototype. | Om jondhale , Aman Dhumal | 31/1/23 | 2023-07-01 | 1 | 100% | bar: WEEK 5 M to WEEK 6 F
1.4 | Designing the Graphical User Interface(GUI) | Aman Dhumal, Pranjal Desai, Dhanashree kasar, Om jondhale | 2023-07-02 | 14/2/23 | 3 | 100% | bar: WEEK 7 M to WEEK 8 F
1.5 | Presentation I | Aman Dhumal, Pranjal Desai, Dhanashree kasar, Om jondhale | 20/2/23 | 27/2/23 | 1 | 100% | bar: WEEK 9 M to WEEK 9 F
2 | Project Design and Implementation
2.1 | Database Design | Aman Dhumal | 27/2/23 | 2023-04-03 | 1 | 100% | bar: WEEK 10 M to WEEK 10 F
2.2 | Database Connectivity of all modules | Aman Dhumal, Pranjal Desai | 2023-04-03 | 2023-11-03 | 1 | 100% | bar: WEEK 11 M to WEEK 11 F
2.3 | Integration of all modules and Report Writing | Aman Dhumal, Pranjal Desai, Dhanashree kasar, Om jondhale | 17/3/23 | 24/3/23 | 1 | 100%
2.4 | Presentation II | Aman Dhumal, Pranjal Desai, Dhanashree kasar, Om jondhale | 31/3/23 | 2023-06-04 | 2 | 100% | bar: WEEK 13 M to WEEK 14 F